## Sheet1
Unit	Number	Issue	Mitigation	Notes	State	Priority	Type
General	2.1.1	Negative edge sensitivity rst	Remove negedg, rst synchronous with clk		Done	Very high	Permanent
General	2.1.2	Harden event generators				Medium
pmu_ahb	2.2.1	Harden external signals AHB bus			Dismissed	Low	Transient
pmu_ahb	2.2.2	SEU on config slv_registers	Added hamming SEC-DEC 32 bit chunks to sll slv_reg		Done	High	Permanent
pmu_ahb	2.2.3	SEU on non-nconfig registers.	Added hamming SEC-DEC 32 bit chunks to sll slv_reg	Transients on dwrite_slave shall be check by software with several reads after write	Done	Medium	Permanent
pmu_ahb	2.2.4	Protect state bits on control state machines	Added triplication to address_pase structure and state signal		Done	High	Permanent
pmu_raw	2.3.1					Low
pmu_raw	2.3.2					High
pmu_raw	2.3.3					Low
pmu_raw	2.3.4
pmu_counters	2.4.1					High
pmu_counters	2.4.2					Low
pmu_counters	2.4.3					High
crossbar	2.5.1					Low
crossbar	2.5.2					Low
MCCU	2.6.1					Medium
MCCU	2.6.2					Low
MCCU	2.6.3					Medium
MCCU	2.6.4			Triplicated quota_int and add voter	Done	High
MCCU	2.6.5			Update_quota_int is protected at the source with hamming. Transients can occur but shall happen at the positive edg of the clock to have effect		Low
MCCU	2.6.6					Low
MCCU	2.6.7					Low
MCCU	2.6.8			Triplicated ccc_suma_int and add voter	Done	High
pmu_overflow	2.7.1		Protected at the source. regs_i on pmu_ahb with hamming		Done	High
pmu_overflow	2.7.2					Low
pmu_overflow	2.7.3		Protected at the source. regs_i on pmu_ahb with hamming		Done	High
pmu_overflow	2.7.4					Low
pmu_overflow	2.7.5					Medium
pmu_overflow	2.7.6		Protected at the source. regs_i on pmu_ahb with hamming		Done	High
pmu_overflow	2.7.7					Medium
pmu_overflow	2.7.8					Medium
pmu_overflow	2.7.9					Low
pmu_overflow	2.7.10					Low
RDC	2.8.1	Enable fail stuck	Source register protected by hamming regs_i[BASE_MCCU_CFG][6]	The source register uses hamming. Errors can afect the unit for one cycle but they will clear by themselves	Done	High
RDC	2.8.2	Transients enable_i induce permanent internal failures	Triplicated enable_i with voter		Done	High
RDC	2.8.3		Triplicated RDC and added output voter	Inputs must be correct, shared among instances	Done	Low
RDC	2.8.4		Triplicated RDC and added output voter	Inputs must be correct, shared among instances	Done	Low
RDC	2.8.5		Triplicated RDC and added output voter	Inputs must be correct, shared among instances	Done	Low
RDC	2.8.6		Triplicated RDC and added output voter	Inputs must be correct, shared among instances	Done	High
RDC	2.8.7		Triplicated RDC and added output voter	Inputs must be correct, shared among instances	Done	High
RDC	2.8.8		Triplicated RDC and added output voter	Inputs must be correct, shared among instances	Done	Medium
RDC	2.8.9		Triplicated RDC and added output voter	Inputs must be correct, shared among instances	Done	High
RDC	2.8.10		Triplicated RDC and added output voter	Inputs must be correct, shared among instances	Done	Low

					Done	Items		Conditions Dcount	13
					19	42		State	Priority
								Done	*High
					Done High prio	Total High
					13	16